## Slide 1
EQUIP Program
Planning & Scheduling Training
April 18, 2023

## Slide 2: Dave Livingston
Group Director of Planning & Scheduling
  Alabama, Tennessee, Texas
B.E. Civ.E.; Vanderbilt University
M.E. Construction Mgmt.; Vanderbilt University
18 years in the Industry
  Precon, Project Mgmt, Planning & Scheduling

## Slide 3: Dan Gilmour
Group Director of Planning & Scheduling
  Carolinas, Georgia, Florida
B.E. Civ.E.; Carnegie Mellon University
16 years in the Industry
  Precon, Project Mgmt, Planning & Scheduling

## Slide 4
Intro to Scheduling & Terminology
Understanding a P6 Schedule
Schedule Development Lifecycle
Maintaining & Updating
Reporting

## Slide 5
INTRO TO scheduling & TERMINOLOGY

## Slide 6: Schedule Development Building Blocks
WBS
Activities
Durations
Relationships

## Slide 7: WBS
Planning Outline | Work Breakdown Structure (WBS)

## Slide 8: WBS and Work Activities
Key Plans create the geographical language in the project schedule
Considerations:
  Areas of similar finish
  Turnover milestones
  Directional workflow
  Equipment
  Safe working conditions
Key Plans

## Slide 9: Activities
What makes an activity?
  Activities consume time
  Activities consume resources
  Activities have a definable start and finish
  Activities are measurable

## Slide 10: Durations
Durations
  Durations should be meaningful
  No dart throws!
  Use quantity take-offs and production rates to calculate durations
  Don’t neglect resource considerations

## Slide 11: Relationships
Types of Relationships
  Physical (hard logic)
  Preferential (soft logic)
    Safety
    Resource
    Access
Types of Relationship Logic
  Finish to Start (FS)
  Start to Start (SS)
  Finish to Finish (FF)
  Start to Finish (SF) – not to be used
In a “complete” network only one activity will not have a predecessor and only one activity will not have a successor

## Slide 12: Scheduling Terms - Relationships
Finish to Start
300
Place Footings
Columns 1 – 7
2
ES EF
LS LF
TF FF
310
Place Footings
Columns 8 - 14
2
ES EF
LS LF
TF FF
320
Place Footings
Columns 15 - 21
2
ES EF
LS LF
TF FF

## Slide 13: Scheduling Terms - Relationships
Start to Start
300
Haul In Structural Fill
10
ES EF
LS LF
TF FF
310
Site Grading
10
ES EF
LS LF
TF FF
320
Building Layout
2
ES EF
LS LF
TF FF

## Slide 14: Scheduling Terms - Relationships
Finish to Finish
300
Haul in Structural Fill
10
ES EF
LS LF
TF FF
310
Site Grading
10
ES EF
LS LF
TF FF
320
Building Layout
2
ES EF
LS LF
TF FF

## Slide 15: Planning Lifecycle

## Slide 16: Scheduling Terms - Dates
Data Date
  The date on which the schedule has been updated to reflect actual progress and upon which the network projects a new completion date.
  The calendar date that separates actual (historical) data from scheduled data. Scheduling software uses the data date to base its network calculations.
Early Start or Finish
  Earliest dates an activity can start and finish once its predecessor network is completed. Activities start as soon as possible if not prevented by logic. Calculated through forward CPM pass.
  Start and Finish on P6 = early dates
Late Start or Finish
  Latest dates an activity can start and finish without delaying the end date of the project. Calculated through backward CPM pass.

## Slide 17: Scheduling Terms - CPM
Data network calculation that considers:
  Activity durations
  Project calendars
  Logic relationships
TO
Conduct a forward calculation through the network
Conduct a backward pass through the network
AND
Establish network paths and timeframes to project completion
Critical Path Method (CPM)

## Slide 18: Scheduling Terms - Float
The amount of time an activity can slip from its Early Start without delaying the project
The difference between an activity’s late dates and early dates
TF = LS – ES
or
TF = LF – EF
Total Float

## Slide 19: Scheduling Terms - Float
Positive Float – activity can be delayed without delaying project completion date
Zero Float (critical) – activity cannot be delayed without delaying project completion date
Negative Float (extremely critical) – activity is behind schedule and has delayed project completion date
Types of Total Float

## Slide 20: Scheduling Terms - Paths
The longest path is the path through the network that establishes the minimum overall project duration.
The critical path can be defined by its amount of float
A project can have multiple critical paths, but only one longest path.
Near critical path
  An activity or set of activities that are almost critical or at risk of becoming critical if delayed past their expected completion times. Inclusion in this list may be made by using total float, longest path value, or multiple critical paths.
Critical Path vs. Longest Path

## Slide 21
schedule development

## Slide 22: Schedule Development Lifecycle
Bid Schedule

## Slide 23: Schedule Development Lifecycle
Initial Baseline Schedule
  Generally due 15 days from NTP
  Full Detail for first 60 days of Construction

## Slide 24: Schedule Development Lifecycle
Baseline Schedule
  Generally due 60 days from NTP, Full Construction Detail

## Slide 25: Schedule Development Lifecycle
Schedule Updates
  At very least, monthly frequency

## Slide 26
understanding a p6 schedule

## Slide 27: Reading a P6 Schedule
Gantt Chart & Timescale
  Data Date - starting point for schedule calculations and it is used to schedule all remaining work.
  Chart Legend
    Level of Effort – Summary Bar
    Actual Work - Past
    Remaining Work – Today / Future
    Critical Activities – Total Float is less than or equal to 0
    Milestone – Point in time
Activity Table
Gant Chart
Time Scale
PAST
FUTURE
Data
Date
WBS
Banding

## Slide 28
managing & updating

## Slide 29: Legal Considerations
In the beginning, the schedule sets the plan.
In the end, the schedule tells the story.

## Slide 30: Legal Considerations
The schedule is the historical record of the project
A Successful Schedule Program:
  Thorough Planning
  Frequent Updates
  Accurate Updates
  Documentation of Changes

## Slide 31: Components of an Update Form
An update form will be filtered to a specific time period from the established data date (i.e. 6-Week Lookahead, 8-Week Lookahead, etc.)
The data date refers to the date of the update. Anything prior to this date will have been started or completed.
Data Date

## Slide 32: Components of an Update Form
The columns found on an update form may be:
  Activity ID
  Activity Name
  Remaining Duration
  New Remaining Duration (not shown above)
  Actual Start
  Actual Finish
  Expected Start
  Expected Finish
Generally, blank cells indicate information needed to update the schedule
Columns

## Slide 33: Filling out an Update Form
Actual Start & Actual Finish: The actual start/finish date of the activity. An “Actual” can not be in the future.
Remaining Duration: If you have started the activity and know how many days it will take to complete, your remaining duration will be days remaining to complete from the data date.
Expected Starts/Finishes: Anticipated future dates.
No Update: This indicates no progress made. When no update is provided, provide an explanation as to why.
Provided update notes may be handwritten or typed, but should be legible and in a different color than the rest of the update form.
Activity Status

## Slide 34: Filling out an Update Form
What does it mean when the data date is moved?
The data date is moved forwards for every update, from the previous update date to the current update date. When your data date moves forwards, anything that has not been started or finished will be affected by this push.
Moving the Data Date

## Slide 35: Proper Update Form

## Slide 36
REPORTING

## Slide 37: Schedule Reports - Lookaheads

## Slide 38: Schedule Reports – Trade Sorts

## Slide 39: Schedule Reports – Scope Sorts

## Slide 40: Schedule Reports – Start Dates

## Slide 41: Schedule Reports – Gannt Chart

## Slide 42: Schedule Reports – Calendar View

## Slide 43: Schedule Reports – Calendar View

## Slide 44: Schedule Reports – Calendar View

## Slide 45
Questions?